## Exec Summary
Rubika Publisher: Professional Web App Roadmap, RFP and Backlog
Goal: move from polished MVP screens to a world-class publishing operating system with brand, campaign, collaboration, reliability, analytics, and reporting depth.
[5 empty] | Phase | Impact | Effort
Current product score 6.8 / 10 | Target product score 9.2 / 10 | Roadmap phases 10 | Backlog items 55 | RFP requirements 42 | Product architecture freeze | 95 | 30
[5 empty] | Brand Kit Pro | 95 | 55
[5 empty] | Campaign OS | 95 | 55
Decision | Recommendation |  |  |  | Composer Studio Pro | 95 | 80
Stop repeating UI polish | Freeze generic visual changes until product architecture, data model, and workflow gaps are implemented. |  |  |  | Planner Pro | 80 | 80
Primary product gap | The app needs brand kit, campaign model, approvals, reliable publish jobs, analytics events, reporting, and team workflows. |  |  |  | Media DAM Pro | 80 | 55
Best theme direction | Light operational SaaS theme: calm canvas, high-contrast surfaces, teal/blue trust accents, restrained motion, selective branded illustrations. |  |  |  | Approvals & Collaboration | 80 | 80
UX direction | Workflow-first: Command Center -> Compose -> Planner -> Campaign -> Queue -> Analytics. Every screen should show state, risk, next action. |  |  |  | Publishing Reliability | 95 | 80
Engineering direction | Build durable domain modules and tests before adding more decoration. Upgrade backend data model in parallel with UI. |  |  |  | Inbox & Engagement | 60 | 80
Launch strategy | Ship in capability releases: brand/campaign, composer/planner, media/reliability, approvals, analytics/reporting. |  |  |  | Analytics, Reporting & AI Optimization | 80 | 80
Phase | Name | Priority | Risk | Definition of done
1 | Product architecture freeze | P0 | Low | Approved PRD, IA map, data model RFC, non-duplicate backlog
2 | Brand Kit Pro | P0 | Medium | Brand settings persisted and applied in composer, previews, dashboard, empty states
3 | Campaign OS | P0 | Medium | Posts belong to campaigns; campaign views drive calendar/content/analytics
4 | Composer Studio Pro | P0 | High | Create-to-schedule workflow under 3 minutes with guardrails and preview
5 | Planner Pro | P1 | High | Planner supports reschedule, filters, inspector, campaign lanes, timezone correctness
6 | Media DAM Pro | P1 | Medium | Every asset shows usage; media can be reused, organized, and validated before publish
7 | Approvals & Collaboration | P1 | High | Create -> review -> approve/reject -> schedule workflow with history
8 | Publishing Reliability | P0 | High | Publish failures are recoverable and auditable; no duplicate sends under retries
9 | Inbox & Engagement | P2 | High | Team can respond, assign, resolve, and measure response time inside app
10 | Analytics, Reporting & AI Optimization | P1 | High | Reports explain what worked, why, and what to do next

## Benchmark
Benchmark Matrix
Competitor capabilities from official/product sources and current Rubika Publisher relative position.
Product | Score | Benchmark strengths | Weakness / caution | What Rubika should learn
Buffer | 8.4 | Clean creator-friendly workflow, scheduling, analytics, engagement, AI assistant, simple reports | Not as enterprise-deep as Sprout/Hootsuite | Clarity, low-friction composer, friendly analytics
Hootsuite | 8.9 | Enterprise publishing, approvals, inbox, listening, reporting, integrations, best-time recommendations | Can feel heavy/complex for smaller teams | Governance, approvals, calendar density, reporting depth
Sprout Social | 9.1 | Publishing, engagement, analytics, listening, workflow management, BI-quality reports | High price/enterprise complexity | Professional analytics, roles, social care, workflow rigor
Later | 8.6 | Visual calendar, media-first planning, link-in-bio, creator commerce workflows | Less enterprise governance than Sprout/Hootsuite | Media-first UX, drag-and-drop planning, lightweight visual delight
Metricool | 8.8 | Planner, analytics, reports, inbox, smartlinks, campaigns, AI analysis, competitor research | Broad scope can make information architecture challenging | All-in-one operational dashboard and report automation
Rubika Publisher current | 6.8 | Single-platform Rubika publishing, media library, calendar, queue, analytics, notifications | Lacks product depth: roles, brand kit, campaigns, approvals, reports, AI, reliability/observability | Strong base, but must move from UI polish to product operating system

## Current Audit
Current Product Audit
Current repo modules and product gaps after recent UI refactors.
Area | Current state | Gap | Workstream
Frontend shell | Partially strong | Premium shell exists but still needs command hierarchy, workspace switching, persistent context, accessibility QA | UI-architecture
Dashboard | Improved | Command center exists; needs role-specific widgets, real KPIs, guided next action, configurable panels | Product/UX
Composer | MVP plus | Needs template engine, brand defaults, AI assist, approval handoff, channel-specific validation, autosave/versioning | Core workflow
Calendar | Improved | Needs drag/drop reschedule, campaign lanes, multi-view density, publish conflict warnings, bulk planning | Planner
Content library | Improved | Rows have visual context; needs saved views, campaign taxonomy, approvals, versions, reusable content ideas | Content ops
Queue | Improved | Needs reliable job state machine, retry policy controls, worker health, publish SLA, dead-letter queue | Reliability
Media | Functional | Needs DAM features: collections, usage map, variants, crop presets, asset review, storage quota | Media ops
Analytics | Improved | Needs true engagement metrics, benchmark comparison, automated reports, campaign ROI, best-time ML | Analytics
Inbox | Prototype | Needs message model, assignments, saved replies, SLA, sentiment, moderation, notifications | Engagement
Backend data model | MVP | Single-store/simple models; needs team, brand, campaign, templates, approvals, audit logs, analytics events | Platform
Security | Basic | Needs RBAC, secret rotation, audit trail, rate limits, encrypted tokens, backup/restore | Platform
Testing/QA | Partial | Frontend check exists; needs backend tests in container, E2E, visual regression, API contract tests | Quality

## 10 Phase Roadmap
10-Phase Refactor Roadmap
Capability-first roadmap to become a professional publishing web app, avoiding repeated UI-only loops.
Phase | Name | Scope | Team | Risk | Priority | Definition of Done
1 | Product architecture freeze | Stop UI loop; define platform domain model, navigation map, information architecture, success KPIs | Product manager, senior full-stack | Low | P0 | Approved PRD, IA map, data model RFC, non-duplicate backlog
2 | Brand Kit Pro | Store logo/avatar, brand colors, voice/tone, CTA presets, hashtag sets, caption/footer defaults | Backend, frontend, UX | Medium | P0 | Brand settings persisted and applied in composer, previews, dashboard, empty states
3 | Campaign OS | Dedicated campaign model, goals, status, content grouping, calendar lanes, campaign analytics | Backend, frontend | Medium | P0 | Posts belong to campaigns; campaign views drive calendar/content/analytics
4 | Composer Studio Pro | Three-pane composer with templates, AI assist, media variants, platform validation, autosave, version history | Frontend, AI/API, backend | High | P0 | Create-to-schedule workflow under 3 minutes with guardrails and preview
5 | Planner Pro | Drag/drop calendar, week/list/month density, conflict warnings, best-time suggestions, bulk scheduling | Frontend, backend | High | P1 | Planner supports reschedule, filters, inspector, campaign lanes, timezone correctness
6 | Media DAM Pro | Collections, tags, usage map, image variants, crop presets, asset health, attachment workflows | Frontend, backend, storage | Medium | P1 | Every asset shows usage; media can be reused, organized, and validated before publish
7 | Approvals & Collaboration | Roles, permissions, approval queues, comments, mentions, reviewer notifications, audit history | Backend, frontend, notifications | High | P1 | Create -> review -> approve/reject -> schedule workflow with history
8 | Publishing Reliability | Worker job model, retries, dead-letter queue, idempotency, health page, SLA alerts, logs that explain recovery | Backend, devops | High | P0 | Publish failures are recoverable and auditable; no duplicate sends under retries
9 | Inbox & Engagement | Message/comment model, unified inbox, assignments, saved replies, SLA, moderation, push/in-app notifications | Backend, frontend | High | P2 | Team can respond, assign, resolve, and measure response time inside app
10 | Analytics, Reporting & AI Optimization | Engagement metrics, campaign reports, export/PDF, benchmark trends, recommendations, listening-lite | Analytics, AI/API, frontend | High | P1 | Reports explain what worked, why, and what to do next
11 | Instagram Publishing Channel | Meta OAuth, Instagram account connection, content publishing containers, queue worker, platform validation, channel analytics | Backend, frontend, devops | High | P0 | Instagram professional account can connect, schedule, publish, retry, audit, and report alongside Rubika

## RFP Requirements
RFP Requirements
Use this sheet as a procurement/specification checklist for implementation, agency review, or internal sprint planning.
ID | Requirement | Acceptance Detail | Priority | Module
FR-001 | Multi-workspace/store management | Users can manage multiple stores/workspaces with clear switching and permissions. | Must | Platform
FR-002 | Brand kit | Workspace stores logo/avatar, brand color, voice, CTA presets, hashtags, footer defaults. | Must | Store
FR-003 | Campaign entity | Campaigns have name, goal, status, dates, budget/notes, content list, analytics rollup. | Must | Campaign
FR-004 | Template library | Reusable post templates for launch, sale, reminder, educational, announcement, support. | Must | Composer
FR-005 | AI writing assistant | Generate, rewrite, shorten, localize, and improve captions based on brand voice. | Should | Composer
FR-006 | Composer validation | Warn on missing media, empty caption, invalid schedule, duplicate hashtags, broken links. | Must | Composer
FR-007 | Autosave and draft recovery | Composer changes persist safely and can be restored after refresh/session loss. | Must | Composer
FR-008 | Version history | Post content changes are versioned with diff and restore. | Should | Content
FR-009 | Media collections | Assets can be organized by folder/collection/campaign and filtered by usage. | Must | Media
FR-010 | Media variants | Support image variants/crop presets optimized for destination surfaces. | Should | Media
FR-011 | Calendar drag/drop | Users can move scheduled posts with drag/drop and confirmation. | Must | Planner
FR-012 | Calendar views | Month, week, list, campaign lane, and status-filtered planner views. | Must | Planner
FR-013 | Best-time suggestions | System suggests publishing windows from history and platform guidance. | Should | Planner/Analytics
FR-014 | Approval workflow | Drafts can be submitted, approved, rejected, edited, and audited. | Must | Collaboration
FR-015 | Role-based access | Admin, editor, reviewer, analyst roles with scoped permissions. | Must | Security
FR-016 | Comments and mentions | Team can comment on posts/assets/campaigns and mention teammates. | Should | Collaboration
FR-017 | Publishing job model | Publishing uses durable jobs with statuses, retries, idempotency keys, and attempt history. | Must | Backend
FR-018 | Worker health | Health dashboard shows worker state, queue depth, errors, and retry controls. | Must | Ops
FR-019 | Dead-letter queue | Failed jobs can be inspected and safely retried/cancelled. | Must | Ops
FR-020 | Operational notifications | In-app/push notifications for failures, approvals, comments, publish success. | Must | Notifications
FR-021 | Unified inbox | Messages/comments appear in one inbox with assignment and resolution state. | Should | Inbox
FR-022 | Saved replies | Workspace can create reusable response templates. | Should | Inbox
FR-023 | Analytics event model | Posts collect publish, failure, engagement, reach/click events where available. | Must | Analytics
FR-024 | Campaign analytics | Campaign view summarizes content output, publish health, engagement, and recommendations. | Must | Analytics
FR-025 | Custom reports | Users can save/export reports by campaign, date range, and status. | Should | Reporting
FR-026 | Audit logs | Sensitive actions and workflow changes are recorded with actor/time/context. | Must | Security
FR-027 | API contract | Backend exposes stable typed API with pagination/filtering/error schema. | Must | Platform
FR-028 | Responsive RTL UI | All screens support Persian RTL, desktop density, tablet and mobile breakpoints. | Must | UX
FR-029 | Accessibility | Keyboard navigation, focus states, contrast, labels, reduced motion support. | Must | UX
FR-030 | Visual design system | Buttons, inputs, tables, cards, charts, tokens, spacing, shadows, motion defined and reused. | Must | Design
NFR-001 | Performance | Key pages load under 2.5s locally with realistic data; tables virtualize above 500 rows. | Must | Quality
NFR-002 | Reliability | No duplicate publishing under retries; publish state transitions are deterministic. | Must | Backend
NFR-003 | Security | Secrets encrypted/masked; tokens rotated; rate limits and auth protection enabled. | Must | Security
NFR-004 | Observability | Structured logs, metrics, health checks, error boundaries, and release diagnostics. | Must | Ops
NFR-005 | Test coverage | Unit, integration, E2E, visual regression, and API contract tests on CI. | Must | Quality
NFR-006 | Data portability | Export posts, media metadata, reports, and audit logs as CSV/XLSX. | Should | Platform
NFR-007 | Scalability | Pagination, background jobs, storage abstraction, and indexed query paths. | Must | Platform
UX-001 | Professional shell | Navigation prioritizes workflows, not pages; command palette and global create remain consistent. | Must | UX
UX-002 | Guided readiness | Every workflow shows what is complete, missing, risky, and next. | Must | UX
UX-003 | Dense but calm tables | Professional tables support thumbnails, saved views, bulk actions, quick filters, inspectors. | Must | UX
UX-004 | Motion language | Use restrained stateful motion for progress, selection, live notifications, and transitions. | Should | UX
UX-005 | Brand expression | Use brand tokens and small branded illustrations/empty states only where they aid comprehension. | Should | Design
FR-044 | Instagram account connection | Workspace can connect, validate, disconnect, and reconnect an Instagram professional account through Meta OAuth. | Must | Publishing
FR-045 | Instagram content publishing | System creates Instagram media containers, publishes them through a durable worker, and records external ids/permalinks. | Must | Publishing
FR-046 | Multi-channel composer | Composer supports Rubika, Instagram, or both with platform-specific validation before scheduling. | Must | Composer
NFR-012 | Credential security | Instagram access tokens are encrypted, scoped, refresh-aware, and never exposed in logs or UI. | Must | Security

## Backlog
Implementation Backlog
Prioritized backlog with phase, epic, effort, dependency, implementation note, and acceptance criteria.
ID | Phase | Epic | Story | Priority | Effort | Dependency | Implementation Notes | Acceptance Criteria
B-001 | 1 | Product | Define PRD and target user roles | P0 | 5 | Product architecture freeze | Document personas, workflows, success KPIs, and out-of-scope items | Approved PRD and backlog baseline
B-002 | 1 | UX | Create app information architecture map | P0 | 5 | Product architecture freeze | Map shell, dashboard, composer, planner, content, media, inbox, analytics | No duplicate routes or repeated CTA patterns
B-003 | 1 | Data | Write domain model RFC | P0 | 8 | Product architecture freeze | Store, user, team, brand kit, campaign, template, approval, job, analytics event | Reviewed schema with migration plan
B-004 | 2 | Backend | Add brand kit fields and migration | P0 | 8 | Brand Kit Pro | Brand colors, logo asset id, voice, CTA, hashtag sets, footer | Store API returns brand kit
B-005 | 2 | Frontend | Brand settings UI | P0 | 8 | Brand Kit Pro | Dedicated section in Store with readiness score | Brand kit can be edited and validated
B-006 | 2 | Frontend | Apply brand kit to composer preview | P0 | 5 | Brand Kit Pro | Avatar/logo, colors, CTA/footer defaults | Preview reflects saved brand kit
B-007 | 2 | Design | Brand empty-state illustration set | P2 | 5 | Brand Kit Pro | Small code-native or generated assets for no media/no campaign/no connection | Used sparingly; no noisy backgrounds
B-008 | 3 | Backend | Campaign model and CRUD API | P0 | 13 | Campaign OS | Campaign status, goals, dates, color, notes, owner | Posts can reference campaign id
B-009 | 3 | Frontend | Campaign workspace | P0 | 13 | Campaign OS | Campaign list, detail, content, calendar, analytics summary | Campaign page is primary planning object
B-010 | 3 | Frontend | Saved views for content table | P1 | 5 | Campaign OS | Save filters by campaign/status/date/owner | Views persist per user
B-011 | 3 | Analytics | Campaign health score | P1 | 5 | Campaign OS | Calculate output, media coverage, schedule health, failure rate | Visible in dashboard and campaign page
B-012 | 4 | Backend | Post template model | P0 | 8 | Composer Studio Pro | Template name, category, prompt, fields, default hashtags, media guidance | Templates API supports CRUD
B-013 | 4 | Frontend | Composer template picker | P0 | 8 | Composer Studio Pro | Launch, sale, reminder, educational, announcement, support templates | Template fills structured composer fields
B-014 | 4 | Frontend | Composer three-pane rebuild | P0 | 13 | Composer Studio Pro | Left assets/templates, center editor, right schedule/preview/readiness | No messy stacked fields
B-015 | 4 | AI | Brand-aware caption assistant | P1 | 13 | Composer Studio Pro | Generate/rewrite caption using store voice and campaign goal | Human confirmation required before apply
B-016 | 4 | Frontend | Composer autosave | P0 | 8 | Composer Studio Pro | Autosave local and server draft state | Refresh restores current draft
B-017 | 4 | Backend | Post version history | P1 | 13 | Composer Studio Pro | Track caption, hashtags, media, schedule changes | Can view diff and restore version
B-018 | 5 | Frontend | Calendar drag/drop reschedule | P0 | 13 | Planner Pro | Drag scheduled posts to new day/time with confirmation | API updates schedule and shows toast
B-019 | 5 | Frontend | Week/day density modes | P1 | 8 | Planner Pro | Compact, comfortable, expanded planner views | No label clipping at desktop/mobile
B-020 | 5 | Backend | Schedule conflict service | P1 | 8 | Planner Pro | Detect too many posts, close times, missing media, connection not ready | Warnings shown before scheduling
B-021 | 5 | Analytics | Best-time recommendation v1 | P1 | 8 | Planner Pro | Use successful publish history and engagement if available | Planner suggests time slots
B-022 | 5 | Frontend | Bulk scheduling workflow | P1 | 8 | Planner Pro | Select multiple drafts, assign campaign/time slots | Multiple posts scheduled with review step
B-023 | 6 | Backend | Media collections model | P1 | 8 | Media DAM Pro | Collections, campaign links, tags, status | Assets grouped beyond folder text
B-024 | 6 | Frontend | Media usage map | P1 | 8 | Media DAM Pro | Show every post/campaign using an asset | No asset can be deleted without usage warning
B-025 | 6 | Frontend | Asset inspector pro | P1 | 8 | Media DAM Pro | Metadata, usage, variants, attach actions, related campaign | One inspector replaces scattered controls
B-026 | 6 | Media | Image crop presets | P2 | 13 | Media DAM Pro | Rubika-ready aspect presets and thumbnails | Generated variant stored with source relation
B-027 | 6 | Backend | Storage abstraction | P1 | 8 | Media DAM Pro | Local now, S3-compatible later | Storage provider can be configured
B-028 | 7 | Backend | Team and roles model | P0 | 13 | Approvals & Collaboration | Users, teams, roles, permissions | Access decisions are server-enforced
B-029 | 7 | Backend | Approval workflow state machine | P0 | 13 | Approvals & Collaboration | Draft, submitted, changes requested, approved, scheduled | Invalid transitions rejected
B-030 | 7 | Frontend | Review queue page | P1 | 8 | Approvals & Collaboration | Reviewer sees pending posts with diff, comments, approve/reject | Review action audited
B-031 | 7 | Collab | Comments and mentions | P1 | 13 | Approvals & Collaboration | Threaded comments on posts/assets/campaigns | Mention triggers notification
B-032 | 7 | Notifications | Approval notifications | P1 | 5 | Approvals & Collaboration | In-app and optional push/email for submission/rejection/approval | Notification links to exact item
B-033 | 8 | Backend | Durable publish job table | P0 | 13 | Publishing Reliability | Job status, idempotency key, attempts, payload hash, scheduled_at | Worker reads jobs not post status alone
B-034 | 8 | Backend | Retry policy engine | P0 | 8 | Publishing Reliability | Configurable retry count, backoff, failure class | Retries do not duplicate messages
B-035 | 8 | Ops | Worker health dashboard | P0 | 8 | Publishing Reliability | Queue depth, last heartbeat, failed jobs, publish latency | Visible from logs/queue
B-036 | 8 | Backend | Dead-letter queue | P0 | 8 | Publishing Reliability | Failed jobs can be inspected, retried, cancelled | No lost failed publish attempts
B-037 | 8 | Quality | Backend test harness fixed in Docker | P0 | 5 | Publishing Reliability | Install pytest path or standard test runner in backend container | Backend tests run in documented command
B-038 | 8 | Quality | Publishing idempotency tests | P0 | 8 | Publishing Reliability | Duplicate retry, timeout, partial success cases | Tests prove no duplicate publish
B-039 | 9 | Backend | Inbox message model | P2 | 13 | Inbox & Engagement | Thread, message, author, status, assignment, source | Inbox has real persisted data
B-040 | 9 | Frontend | Unified inbox rebuild | P2 | 13 | Inbox & Engagement | Queues, assignments, saved replies, resolution states | Can process messages from one screen
B-041 | 9 | Collab | Saved replies | P2 | 5 | Inbox & Engagement | Workspace response templates with variables | Can insert reply with preview
B-042 | 9 | Analytics | Response SLA metrics | P2 | 8 | Inbox & Engagement | Response time, unresolved, assignment load | Inbox dashboard has SLA status
B-043 | 10 | Backend | Analytics event model | P1 | 13 | Analytics & Reporting | Event type, metric, post, campaign, source, timestamp | Reports use event model not raw attempts only
B-044 | 10 | Frontend | Report builder v1 | P1 | 13 | Analytics & Reporting | Date range, campaign, status, metrics, export | User can save report config
B-045 | 10 | Reporting | PDF/XLSX export | P1 | 8 | Analytics & Reporting | Branded reports with summary and tables | Export matches selected filters
B-046 | 10 | AI | Insight recommendations | P2 | 13 | Analytics & Reporting | Explain best content, risks, suggested next actions | Recommendations cite source metrics
B-047 | 10 | Benchmark | Competitor/listening-lite tracker | P3 | 13 | Analytics & Reporting | Manual competitor accounts/topics and trend notes | Campaign planning can reference market observations
B-048 | Cross | UX | Accessibility audit and fixes | P0 | 8 | Design System | Keyboard, focus, ARIA, contrast, reduced motion | Pass agreed accessibility checklist
B-049 | Cross | Design | Component inventory consolidation | P0 | 8 | Design System | Button, input, table, panel, modal, tag, chart, inspector | No duplicate one-off component styles
B-050 | Cross | Quality | E2E smoke tests | P0 | 13 | Quality | Login, store setup, media upload, compose, schedule, queue, analytics | CI runs E2E smoke suite
B-051 | Cross | Quality | Visual regression screenshots | P1 | 8 | Quality | Dashboard, composer, calendar, content, queue, analytics | Detect major layout regressions
B-052 | Cross | Platform | Pagination and search API | P1 | 8 | Platform | Server-side filtering/sorting for posts/media/campaigns | Large datasets do not slow UI
B-053 | Cross | Security | Secret management upgrade | P0 | 8 | Security | Encrypted bot tokens, masking, rotation support | Secrets never returned plaintext
B-054 | Cross | Ops | Backup and restore procedure | P1 | 8 | Operations | Database/media backup scripts and restore test | Restore tested on local environment
B-055 | Cross | Docs | Runbook and onboarding docs | P1 | 5 | Operations | Dev setup, Docker, testing, publishing recovery | New engineer can run app and tests
B-057 | 11 | Instagram Connection | Create Meta OAuth connection flow and Instagram account model | P0 | 13 | Publishing Reliability | Use Meta app OAuth, store encrypted tokens, account/page identifiers, expiry, reconnect and disconnect flows | Workspace can connect and validate an Instagram professional account
B-058 | 11 | Instagram Publishing | Publish scheduled posts to Instagram through worker jobs | P0 | 21 | B-057, worker reliability | Create media container, poll readiness when needed, publish container, store external id/permalink, classify errors | Scheduled Instagram post publishes once with auditable job state
B-059 | 11 | Platform Validation | Add Instagram validation to composer and media editor | P0 | 8 | Media DAM Pro, Composer Studio Pro | Validate format, aspect ratio, file type, caption, channel selection, and export readiness before scheduling | Invalid Instagram posts are blocked before queueing
B-060 | 11 | Channel Analytics | Add Instagram channel filters and published id metrics | P1 | 13 | Analytics events | Capture published id/permalink and channel-specific event metadata for reports and filters | Content, queue, logs, calendar, and analytics can filter Instagram posts

## UI UX System
UI / UX Design System Roadmap
Design the product as a professional operational tool: dense, clear, branded, accessible, and guided.
Area | Target Pattern | Detailed Direction | Implementation Notes
Navigation | Workflow-first shell | Primary nav: Command Center, Compose, Planner, Campaigns, Content, Media, Inbox, Analytics, Settings | Active state, command palette, global create, workspace switcher
Tables/lists | Operational data views | Thumbnails, campaign markers, saved views, bulk actions, sticky inspector | Used in Content, Queue, Logs, Campaigns, Media
Composer | Studio layout | Three-pane workspace with template/media, editor, schedule/preview/readiness | Avoid stacked cards and scattered fields
Planner | Professional calendar | Month/week/list/lane modes, drag/drop, compact toolbar, right inspector | Best-time and conflict warnings
Inspectors | Context panels | Show preview, status, actions, audit/recovery hints | Consistent across content, queue, media, campaign
Forms | Quiet enterprise controls | Grouped fields, inline validation, examples, required indicators | No oversized empty boxes
Analytics | Insight board | Narrative metrics, top content, campaign health, chart drilldown | Show next action, not only numbers
Motion | Purposeful motion | Live pulse, selection, transitions, progress, toast; reduced motion safe | No decorative noise
Empty states | Branded helpful states | Small spot illustration plus action; show why empty and what next | No generic template cards
Accessibility | Professional default | Keyboard flow, visible focus, labels, high contrast, RTL reading order | Verified before release

## Theme Direction
Theme and Brand Direction
Recommended visual language: light, trustworthy, operational, calm, and brand-ready. Avoid black-heavy or noisy decorative themes.
Token / Layer | Value | Purpose | Usage Guidance
Canvas | #F5F8FA | Soft operational canvas | Use for app background, not as a decorative pattern
Surface | #FFFFFF | Primary panels/cards/tables | High contrast with subtle hairline borders
Text | #17313B | Main readable ink | Avoid pure black-heavy theme for this user class
Muted text | #5D7280 | Secondary labels | Keep readable at 12px+
Primary | #0F766E | Trust/operation/brand signal | Buttons, active states, chart primary
Blue | #2563EB | Information and focus | Links, selected states, command actions
Success | #15803D | Ready/published/safe | Status only; do not flood pages green
Warning | #B7791F | Needs attention | Schedule warnings, missing media
Danger | #C24150 | Failure/recovery | Errors, failed publish states
Radius | 6-8px | Professional product feel | Avoid pill/card excess unless chips/tokens
Shadow | hairline + soft lift | Depth without floating-card chaos | Panels remain calm and aligned
Pattern/art | Selective | Use product-specific visual maps, not generic dots/blobs | Only where it explains workflow or brand

## User Journeys
Professional User Journeys
Workflows that should define the app experience and acceptance testing.
Journey | User Goal | Current Gap | Professional Future State | Success Metrics
Owner onboarding | New user creates workspace, brand, Rubika connection | Store setup exists but brand readiness and guided setup are shallow | Step-by-step readiness with tests, brand kit, sample post, first schedule | Activation rate, time to first scheduled post
Create and schedule | User needs post from idea to scheduled content | Composer works but lacks templates, autosave, validation, approval handoff | Template -> media -> caption -> preview -> readiness -> schedule in one flow | Create time, validation errors, abandonment
Plan campaign | User wants a week/month campaign | Campaign is plain text on posts | Campaign object with goals, calendar lanes, content list, health, analytics | Campaign completion, publish consistency
Recover failed publish | Worker/API failure needs safe recovery | Queue/logs improved but job model is shallow | Failure classification, recovery hint, retry policy, dead-letter queue | Recovery time, duplicate sends
Manage media | User organizes product images | Media has folder/tags but no full DAM | Collections, usage map, crop variants, attachment inspector | Asset reuse, missing-media rate
Approve content | Team/client must review before publishing | No roles/approval model | Submit, comment, approve/reject, schedule, audit | Approval cycle time
Measure performance | User wants to know what worked | Analytics uses publish attempts and local context | Engagement/campaign reports, export, recommendations | Report usage, action completion
Respond to audience | User handles comments/messages | Inbox is prototype-like | Unified inbox, assignments, saved replies, SLA | Response time, unresolved messages

## Architecture
Architecture and Data Roadmap
Move from page-level MVP to durable product modules.
Type | Module / Entity | Current or Proposed Fields | Current Gap | Next Architecture Step
Current | User | email, password, full_name | Single active user concept | Add teams, roles, invitations
Current | Store | name, category, phone, description, default_hashtags, footer, timezone | Good seed for brand kit | Extend to BrandKit or brand fields
Current | RubikaAccount | bot_token, chat_id, status, last_error | Basic connection state | Encrypt, rotate, audit connection tests
Current | Post | title, caption, hashtags, status, campaign string, schedule timestamps | Core content record | Add campaign_id, approval_status, owner, versioning
Current | MediaAsset | post_id, filename, path, content_type, folder, tags | Basic library | Collections, variants, usage, storage provider
Current | PublishAttempt | post_id, action, status, payloads, error, timestamps | Useful logs | Add durable PublishJob, attempt relationship, idempotency
Proposed | Campaign | store_id, name, goal, status, date range, color, owner | Missing | Foundation for planning and reporting
Proposed | Template | category, fields, prompt, default copy, media guidance | Missing | Foundation for composer speed
Proposed | Approval | post_id, submitter, reviewer, state, comments, timestamps | Missing | Foundation for team governance
Proposed | Notification | actor, recipient, type, severity, action_url, read_at | Derived now | Persist and support push/in-app
Proposed | AnalyticsEvent | source, metric, value, post_id, campaign_id, timestamp | Missing | Foundation for real reports
Proposed | AuditLog | actor, action, resource, before/after, timestamp | Missing | Security and compliance

## Release KPI
Release Plan and KPIs
A practical sequence for shipping the professional rebuild without losing restore checkpoints.
Release | Timing | Theme | Scope | Exit KPI
R0 | Now | Stabilize current branch | All checks pass, no dirty worktree, current UI committed/pushed | Build green, browser smoke
R1 | Weeks 1-2 | Product architecture + brand kit | PRD/RFC, brand model, store UI, brand preview defaults | Time to first branded post < 10 min
R2 | Weeks 3-5 | Campaign OS + Composer Pro | Campaign model, templates, studio layout, validation, autosave | Create-to-schedule < 3 min
R3 | Weeks 6-8 | Planner + media DAM | Drag/drop planner, collections, usage map, crop variants | Missing-media rate down 50%
R4 | Weeks 9-11 | Approvals + reliability | Roles, review queue, publish jobs, retry/dead-letter, health | Duplicate publish rate = 0
R5 | Weeks 12-14 | Analytics/reporting + inbox v1 | Event model, report builder/export, unified inbox skeleton | Report generated in < 2 min
R6 | Weeks 15-16 | Hardening and launch | E2E, visual regression, accessibility, docs, backup/restore | Release candidate accepted
Quality Gates: every release must include npm check, backend compile/test path, browser smoke, migration verification, and GitHub push checkpoint.

## Sources
Sources and Assumptions
Benchmarks use current official/product pages and local repo inspection. This is a roadmap document, not a legal procurement contract.
Source | URL | Used for
Hootsuite Platform | https://www.hootsuite.com/platform | All-in-one scheduling, analytics, engagement, listening, AI, approvals, benchmarking.
Hootsuite Approval Workflow | https://www.hootsuite.com/platform/social-media-approval-tool | Create, approve, post workflow; approvals by role; history and notifications.
Hootsuite Publish | https://www.hootsuite.com/platform/publish | Calendar/list views, bulk scheduling, approval workflow, best-time recommendations.
Buffer overview | https://support.buffer.com/article/598-what-is-buffer-and-where-can-i-watch-a-demo | Small-business scheduling, analytics, engagement, post breakdown, custom reports.
Buffer analytics | https://support.buffer.com/article/602-getting-started-with-buffers-analytics-features | Channel-level and high-level analytics in one glance.
Sprout Social features | https://sproutsocial.com/features/ | Publishing, workflow, analytics, response benchmarks, tracking codes, listening.
Sprout Listening | https://support.sproutsocial.com/hc/en-us/articles/115005498146-Introduction-to-Listening | Listening widgets, topics, trends, sentiment, report builder.
Later Scheduler | https://later.com/social-media-scheduler/ | Visual scheduling, link in bio, multi-brand workflow, analytics.
Later Calendar Help | https://help.later.com/hc/en-us/sections/1500000593001-Calendar-Features | Best time to post, profile switching, timezone/calendar workflow.
Metricool Platform | https://metricool.com/ | Planner, analytics, reporting, inbox, smartlinks, campaigns, AI analysis.
Metricool Planner | https://metricool.com/planner/ | Planner, calendar filters, platform presets, approval system, collaborative notes.
Assumption | Detail | Impact
Current score | 6.8/10 based on visible product depth after recent UI refactors. | Useful directional benchmark, not a market survey score.
Target score | 9.2/10 assumes durable workflows, reliability, reporting, collaboration, and brand system are completed. | Requires backend/data work, not just UI.
Rubika integration | Roadmap treats Rubika as primary platform while leaving room for future multi-channel architecture. | Prioritize single-platform depth first.
Team size | Assumes 1-3 engineers plus product/design support; timeline should expand if only one part-time developer. | Adjust release timing based on capacity.
Meta Instagram Platform Content Publishing | https://developers.facebook.com/docs/instagram-platform/content-publishing/ | Official reference for Instagram Graph API content publishing flow; re-check at implementation time.